## Sheet1
No | Date | Region | Area | OA Workshop Location | Agenda | Participants | ITR3A Project Team | Status
1 | 2017-08-08 | West Java | - Region West Java HO - Zone Operation 1 - Zone Operation 2 - Branch BSD - Branch Bandung - Branch Batam - Branch Karimun - DTS - Branch Tanjung Priuk - Branch Cirebon - Branch Cilegon | BSD Office | 09:00 - 09.30: Update ITR3A Project | 1. GM Java (Optional) 2. Region Manager 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Hub Operation Manager 8. Area PS Manager 9. Area Finance Mangager 10. HC Region/Area | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Achmad Audy, Iwan Fauzan, Ridwan, Endah - Functional Lead: Pudjo, Rudi Pais, Aswin, Alfian, Alimudin, Lies - PM: Fama Flora | Not Started
[5 empty] | 09:30 - 10:30: Organization Alignment Customer Support | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Hub Operation Manager 8. HC Region/Area Representative
[5 empty] | 10:30 - 11:30: Organization Alignment Supply Chain | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. Hub Operation Manager 7. HC Region/Area Representative
[5 empty] | 13:00 - 14:00: Organization Alignment Sales & Marketing | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Area PS Manager 8. HC Region/Area Representative
[5 empty] | 14:00 - 15:00: Organization Alignment Finance | 1. GM Java (Optional) 2. Region Manager (Optional)' 3. Area Finance Manager 4. HC Region/Area Representative
2 | 2017-08-09 | East Java | - Region East Java HO - Zone Operation 1 - Zone Operation 2 - Branch Mataram - Branch Denpasar - Branch Kupang - Branch Semarang - Branch Surabaya - Branch Cilacap - PLTU Batang - TumpangPItu - Kupang-Waingapu | Surabaya Office | 09:00 - 09.30: Update ITR3A Project | 1. Region Manager 2. Zone Operation Head 3. SCC Head 4. Hub Operation Manager 5. Area PS Manager 6. Area Finance Mangager 7. HC Region/Area | - CM Core: Nia, Ali Zulfikar - Functional Lead: Rudi Pais - CM Function: Webex - PM: ??? | Not Started
[5 empty] | 09:30 - 10:30: Organization Alignment Customer Support | 1. Region Manager (Optional) 2. Zone Operation Head 3. SCC Head 4. Hub Operation Manager 5. HC Region/Area Representative
[5 empty] | 10:30 - 11:30: Organization Alignment Supply Chain | 1. Region Manager (Optional) 2. Zone Operation Head 3. Hub Operation Manager 4. HC Region/Area Representative
[5 empty] | 13:00 - 14:00: Organization Alignment Sales & Marketing | 1. Region Manager (Optional) 2. Zone Operation Head 1 3. SCC Head 4. Area PS Manager 5. HC Region/Area Representative
[5 empty] | 14:00 - 15:00: Organization Alignment Finance | 1. Region Manager (Optional) 2. Area Finance Manager 3. HC Region/Area Representative
3 | 2017-08-11 | North Sumatera | - Region North Sumatera HO - Zone Operation - ROH Padang - ROH Duri - ROH Pekanbaru - ROH Martabe - ROH Banda Aceh - ROH Medan | Padang Office | 14:00 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Region Manager - Zone Operation Head - Representative Head - Hub Operation Manager - Area Finance Mangager - SCC Head - Area PS Manager - HC Region/Area | - CM Core: Marjuang, Zulfiadi - CM Function: Webex - Functional Lead: Alimudin Aswin - PM: ??? | Not Started
4 | 2017-08-11 | South Sumatera | - Region South Sumatera HO - Zone Operation 1 - ROH Palembang - ROH Tanjung Enim - ROH Jambi - ROH Bengkulu - ROH Bandar Lampung - ROH Prabumulih - ROH Bangka Belitung | Palembang Office | 13:00 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Region Manager - Zone Operation Head - Representative Head - Hub Operation Manager - Area Finance Mangager - SCC Head - Area PS Manager - HC Region/Area | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - Functional Lead: Aswin - PM/Integration: Flora | Not Started
5 | 2017-09-05 | TTD | - Region TTD - Service Support Grasberg - Service Operation UG - Service Operation Haul Truck - Service Operation HSE - MRC - CRC - Parts Operation & Distribution HOBU | Tembagapura | 09:00 - 16:30: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - GM TTD - Manager Area Service - Manager Grasberg Ops - GOM LOBU - GOM Underground Ops - Manager Service Ops UG - Manager Technology - Manager Finance & Contract Mgmt - Manager Customer Service - HC Region/Area | - CM Core: Zulfiadi, Marjuang - Functional Lead: Pudjo Harsono - PM: Fama Flora | Not Started
6 | TBD | TBHD | - Region TBHD | Mataram | TBD | - GM Batuhijau - EM Manager - Technical Support Manager - Parts Operation Manager - Area Service Manager - Finance Manager - HC Region/Area | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - Integration: Widodo - PM: Fama Flora | Not Started
7 | 2017-08-15 | North Kalimantan | - North Kal HO - Branch Samarinda - Separi - Melak - Balikpapan - Tj. Redeb - Berau - Tarakan - Sanga-Sanga - Sangata | Balikpapan HO | 08:30 - 12:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - GM North Kal - EM Manager - Service Manager - Technical Support Manager - CSPT Manager - Branch Manager/Head - GOM Sangata - Finance Manager - Area PS Sales Manager - HC Region/Area | - CM Core: Zulfiadi, Marjuang - CM Function: Webex - Integration: Widodo - PM: Fama Flora | Not Started
|  | CRC & SOS | - CRC - SOS | Balikpapan HO | 13:30 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Technical Support Manager (CRC Group) - Technical Support Manager - Parts Manager - Production Manager - Financial Controller - SOS Manager |  | Not Started
8 | TBD | South Kalimantan | - South Kal HO - Branch Banjarmasin - Branch Batu Licin - Branch Pontianak - Tanjung Site - Batu Kajang - Pangkalan Bun | Banjarmasin HO | TBD | - GM South Kal - PS Manager - Area EM Manager - Area Service Manager - Area Parts Manager - GOM Retail HUB - GOM Mining HUB - Branch Manager/Head - Finance Manager - Area PS Sales Manager - HC Region/Area - Region Manager | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - Functional Lead: Pudjo Harsono - PM: ??? Flora | Not Started
9 | TBD | East Indonesia | - Region EIA HO - Region Makasar - Region Manado - Region Soroako - Region Sorong - Branch Palu - Branch Kendari - Branch Luwuk - Branch Ambon - Branch Monokwari - Branch Merauke - Branch Nabire - Branch Jayapura - Service - Parts Operation - Equipment Management | Makassar HO | TBD | - GM - Region Manager - Area Finance Manager - Area PS Sales Manager - Branch Head - HC Region/Area | - CM Core: Zulfiadi, Ali Zulfikar - CM Function: Webex - Functional Lead: Alfian Alimuddin - PM: ??? | Not Started
10 | TBD | PS Sales, PSM HO | Supply Chain: - Special Product Supply Planning & Proc. - CAT Supply Planning - S&P Sales & Marketing: - Product Support Marketing - CRM - Product Support Sales Finance: - GA & Reporting - AR & AP - Tax Management & Operation - Corporate Treasury - FICO | Jakarta HO | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Ridwan - Functional Lead: Alimudin - Integration: Widodo | Not Started
11 | TBD | PSC HO | - CRC - SOS | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Iwan Fauzan - Functional Lead: Rudi Pais - PM/Integration: Fama Flora | Not Started
11 | TBD | S&P | - CRC - SOS | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: All - Functional Lead: Lies Windarti Alfian - PM: Fama Flora | Not Started
12 | 2017-08-29 | FI - HO | - TUS - Sales & Marketing - Parts - FICO | HO - Jakarta | 09:00 - 11:00 |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Endah - Functional Lead: Aswin - PM/Integration: Fama Flora | Not Started
13 | TBD | CS - HO |  | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Achmad Audy - Functional Lead: Lies Windarti, Pjo Harsono - PM: Fama Flora | Not Started
14 | 2017-08-30 | TUS | - TUS - Sales & Marketing - Parts - FICO | Webex | TBD | - TUS GM - Parts Manager - Sales & Marketing Div Manager - Financial Controller | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: All - Functional Lead: Aswin - PM: Fama Flora | Not Started

## Sheet1 (2)
No | Date | Region | Area | OA Workshop Location | Agenda | Participants | ITR3A Project Team | Status
1 | 2017-08-08 | West Java | - Region West Java HO - Zone Operation 1 - Zone Operation 2 - Branch BSD - Branch Bandung - Branch Batam - Branch Karimun - DTS - Branch Tanjung Priuk - Branch Cirebon - Branch Cilegon | BSD Office | 09:00 - 09.30: Update ITR3A Project | 1. GM Java (Optional) 2. Region Manager 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Hub Operation Manager 8. Area PS Manager 9. Area Finance Mangager 10. HC Region/Area | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Achmad Audy, Iwan Fauzan, Ridwan, Endah - Functional Lead: Pudjo, Rudi Pais, Aswin, Alfian, Alimudin, Lies - PM: Flora | Not Started
[5 empty] | 09:30 - 10:30: Organization Alignment Customer Support | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Hub Operation Manager 8. HC Region/Area Representative
[5 empty] | 10:30 - 11:30: Organization Alignment Supply Chain | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. Hub Operation Manager 7. HC Region/Area Representative
[5 empty] | 13:00 - 14:00: Organization Alignment Sales & Marketing | 1. GM Java (Optional) 2. Region Manager (Optional) 3. Zone Operation Head 1 4. Zone Operation Head 2 5. Branch Head Batam 6. SCC Head 7. Area PS Manager 8. HC Region/Area Representative
[5 empty] | 14:00 - 15:00: Organization Alignment Finance | 1. GM Java (Optional) 2. Region Manager (Optional)' 3. Area Finance Manager 4. HC Region/Area Representative
2 | 2017-08-09 | East Java | - Region East Java HO - Zone Operation 1 - Zone Operation 2 - Branch Mataram - Branch Denpasar - Branch Kupang - Branch Semarang - Branch Surabaya - Branch Cilacap - PLTU Batang - TumpangPItu - Kupang-Waingapu | Surabaya Office | 09:00 - 09.30: Update ITR3A Project | 1. Region Manager 2. Zone Operation Head 3. SCC Head 4. Hub Operation Manager 5. Area PS Manager 6. Area Finance Mangager 7. HC Region/Area | - CM Core: Nia, Ali Zulfikar - Functional Lead: Rudi Pais - CM Function: Webex | Not Started
[5 empty] | 09:30 - 10:30: Organization Alignment Customer Support | 1. Region Manager (Optional) 2. Zone Operation Head 3. SCC Head 4. Hub Operation Manager 5. HC Region/Area Representative
[5 empty] | 10:30 - 11:30: Organization Alignment Supply Chain | 1. Region Manager (Optional) 2. Zone Operation Head 3. Hub Operation Manager 4. HC Region/Area Representative
[5 empty] | 13:00 - 14:00: Organization Alignment Sales & Marketing | 1. Region Manager (Optional) 2. Zone Operation Head 1 3. SCC Head 4. Area PS Manager 5. HC Region/Area Representative
[5 empty] | 14:00 - 15:00: Organization Alignment Finance | 1. Region Manager (Optional) 2. Area Finance Manager 3. HC Region/Area Representative
3 | 2017-08-11 | North Sumatera | - Region North Sumatera HO - Zone Operation - ROH Padang - ROH Duri - ROH Pekanbaru - ROH Martabe - ROH Banda Aceh - ROH Medan | Padang Office | 14:00 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Region Manager - Zone Operation Head - Representative Head - Hub Operation Manager - Area Finance Mangager - SCC Head - Area PS Manager - HC Region/Area | - CM Core: Marjuang, Zulfiadi - CM Function: Webex - Functional Lead: Aswin | Not Started
4 | 2017-08-11 | South Sumatera | - Region South Sumatera HO - Zone Operation 1 - ROH Palembang - ROH Tanjung Enim - ROH Jambi - ROH Bengkulu - ROH Bandar Lampung - ROH Prabumulih - ROH Bangka Belitung | Palembang Office | 13:00 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Region Manager - Zone Operation Head - Representative Head - Hub Operation Manager - Area Finance Mangager - SCC Head - Area PS Manager - HC Region/Area | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - PM/Integration: Flora | Not Started
5 | 2017-09-05 | TTD | - Region TTD - Service Support Grasberg - Service Operation UG - Service Operation Haul Truck - Service Operation HSE - MRC - CRC - Parts Operation & Distribution HOBU | Tembagapura | 09:00 - 16:30: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - GM TTD - Manager Area Service - Manager Grasberg Ops - GOM LOBU - GOM Underground Ops - Manager Service Ops UG - Manager Technology - Manager Finance & Contract Mgmt - Manager Customer Service - HC Region/Area | - CM Core: Zulfiadi, Marjuang - Functional Lead: Pudjo Harsono - PM: Flora | Not Started
6 | TBD | TBHD | - Region TBHD | Mataram | TBD | - GM Batuhijau - EM Manager - Technical Support Manager - Parts Operation Manager - Area Service Manager - Finance Manager - HC Region/Area | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - Integration: Widodo - | Not Started
7 | 2017-08-15 | North Kalimantan | - North Kal HO - Branch Samarinda - Separi - Melak - Balikpapan - Tj. Redeb - Berau - Tarakan - Sanga-Sanga - Sangata | Balikpapan HO | 08:30 - 12:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - GM North Kal - EM Manager - Service Manager - Technical Support Manager - CSPT Manager - Branch Manager/Head - GOM Sangata - Finance Manager - Area PS Sales Manager - HC Region/Area | - CM Core: Zulfiadi, Marjuang - CM Function: Webex - Integration: Widodo - PM: Flora | Not Started
|  | CRC & SOS | - CRC - SOS | Balikpapan HO | 13:30 - 17:00: Update ITR3A Project, Organization Alignment FI, CS, SC, SM | - Technical Support Manager (CRC Group) - Technical Support Manager - Parts Manager - Production Manager - Financial Controller - SOS Manager |  | Not Started
8 | TBD | South Kalimantan | - South Kal HO - Branch Banjarmasin - Branch Batu Licin - Branch Pontianak - Tanjung Site - Batu Kajang - Pangkalan Bun | Banjarmasin HO | TBD | - GM South Kal - PS Manager - Area EM Manager - Area Service Manager - Area Parts Manager - GOM Retail HUB - GOM Mining HUB - Branch Manager/Head - Finance Manager - Area PS Sales Manager - HC Region/Area - Region Manager | - CM Core: Nia, Ali Zulfikar - CM Function: Webex - PM: Flora | Not Started
9 | TBD | East Indonesia | - Region EIA HO - Region Makasar - Region Manado - Region Soroako - Region Sorong - Branch Palu - Branch Kendari - Branch Luwuk - Branch Ambon - Branch Monokwari - Branch Merauke - Branch Nabire - Branch Jayapura - Service - Parts Operation - Equipment Management | Makassar HO | TBD | - GM - Region Manager - Area Finance Manager - Area PS Sales Manager - Branch Head - HC Region/Area | - CM Core: Zulfiadi, Ali Zulfikar - CM Function: Webex - Functional Lead: Alimuddin | Not Started
10 | TBD | PS Sales, PSM HO | Supply Chain: - Special Product Supply Planning & Proc. - CAT Supply Planning - S&P Sales & Marketing: - Product Support Marketing - CRM - Product Support Sales Finance: - GA & Reporting - AR & AP - Tax Management & Operation - Corporate Treasury - FICO | Jakarta HO | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Ridwan - Functional Lead: Alimudin - Integration: Widodo | Not Started
11 | TBD | PSC HO | - CRC - SOS | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Iwan Fauzan - Functional Lead: Rudi Pais - PM/Integration: Widodo | Not Started
11 | TBD | S&P | - CRC - SOS | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: All - Functional Lead: Alfian - PM: Widodo | Not Started
12 | 2017-08-29 | FI - HO | - TUS - Sales & Marketing - Parts - FICO | HO - Jakarta | 09:00 - 11:00 |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Endah - Functional Lead: Aswin - PM/Integration: Fama Flora | Not Started
13 | TBD | CS - HO |  | HO - Jakarta | TBD |  | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: Achmad Audy - Functional Lead: Lies Windarti, Pujo Harsono - PM: Fama Flora / Widodo | Not Started
14 | 2017-08-30 | TUS | - TUS - Sales & Marketing - Parts - FICO | Webex | TBD | - TUS GM - Parts Manager - Sales & Marketing Div Manager - Financial Controller | - CM Core: Nia Kaniawati, Zulfiadi, Marjuang, Ali - CM Function: All - Functional Lead: Aswin, Rudi - PM: Fama Flora / Widodo | Not Started