## UAT_Legend
No | Scenario | Scenario Description | Dry Run Start Date | UAT Start Date | DR to Execution (Days)
1 | UAT-CS-001 | PDI & Asset Hand Over, includes PIP | 1900-01-01 | 2018-02-26 | 2018-02-27
2 | UAT-CS-002 | Standard Warranty | 1900-01-02 | 2018-02-28 | 2018-03-02
3 | UAT-CS-003 | Flat Rate using Merchandising Program | 1900-01-01 | 2018-03-05 | 2018-03-06
4 | UAT-CS-004 | Strip & Quote with Inter Branch Job | 1900-01-02 | 2018-03-07 | 2018-03-09
5 | UAT-CS-005 | MARC Contract | 1900-01-01 | 2018-02-19 | 2018-02-20
6 | UAT-CS-006 | Post MARC | 1900-01-02 | 2018-02-21 | 2018-02-23
7 | UAT-CS-007 | CSA by Event | 1900-01-01 | 2018-03-12 | 2018-03-13
8 | UAT-CS-008 | CSA by Fix Amount | 1900-01-01 | 2018-03-15 | 2018-03-16
9 | UAT-CS-009 | Component Rebuild Center | 1900-01-01 | 2018-02-12 | 2018-02-13
10 | UAT-CS-010 | Machine Rebuild Center | 1900-01-01 | 2018-02-14 | 2018-02-15
11 | UAT-CS-011 | Machine rebuild KK / Workshop major rebuild | 1900-01-01 | 2018-02-26 | 2018-02-27
12 | UAT-CS-012 | Rental Repair & Maintenance | 1899-12-31 | 2018-02-23 | 2018-02-23
13 | UAT-CS-013 | TCCRP Warranty Process | 1899-12-31 | 2018-02-13 | 2018-02-13
14 | UAT-PSL-001 | Parts Sales - Credit (CAT & non-CAT), Committed Demand | 1900-01-01 | 2018-03-01 | 2018-03-02
15 | UAT-PSL-002 | Parts Sales - Credit - TUS | 1899-12-31 12:00 | 2018-02-19 | 2018-02-20
16 | UAT-PSL-003 | Parts Sales - Cash (Premium, Reman/Reman Local, , used part, salvage) | 1899-12-31 12:00 | 2018-03-07 | 2018-03-08
17 | UAT-PSL-004 | Parts Sales - Parts Store (PSIP) | 1899-12-31 | 2018-02-28 | 2018-02-28
18 | UAT-PSL-005 | Parts Sales - PEX | 1900-01-01 | 2018-03-05 | 2018-03-06
19 | UAT-PSL-006 | Parts Sales - DDU | 1899-12-31 12:00 | 2018-02-12 | 2018-02-13
20 | UAT-PSL-007 | Parts Sales - DDP / TUS - KPC | 1899-12-31 12:00 | 2018-02-21 | 2018-02-22
21 | UAT-PSL-008 | Parts Sales - Consignment | 1899-12-31 12:00 | 2018-02-14 | 2018-02-15
22 | UAT-PSL-009 | Parts Sales - Consolidate Invoice (Stockless) | 1899-12-31 12:00 | 2018-02-23 | 2018-02-26
23 | UAT-PSC-001 | PRA | 1899-12-31 | 2018-03-14 | 2018-03-14
24 | UAT-PSC-002 | Tools End to End (CAT - Asset) | 1899-12-31 | 2018-03-09 | 2018-03-09
25 | UAT-FIN-001 | Month End Closing | 1900-01-02 | 2018-03-14 | 2018-03-16
26 | UAT-FIN-002 | Seeding for Rotable Components (PEX, MARC, Strategic Customer) | 1900-01-01 | 2018-03-12 | 2018-03-13

## UAT Schedule by User
Name | Position | Office | Scenario | Duration (Day) | UAT Start Date | UAT End Date | time axis 2018-02-05 to 2018-03-30
Abdul Asis | Counterman | Sanggata - North Kalimantan | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Acnes Radeg Mustika Kaltim | Office Operation Assistant | Kalimantan Operations - EMP | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Ade Candra | Event Planner | SCC North Sumatra | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Afifan Yunaini Satria Pratama | Parts Advisor | SCC North Sumatra | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Akhmar Walessa | Senior Analyst Finance | Pekanbaru | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Andhik Pujianto | Sales Supervisor | Surabaya | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Ani Atiah Dwi S. | Sr. Analyst - AR & AP Accounting | HO | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Ani Atiah Dwi S. | Sr. Analyst - AR & AP Accounting | HO | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Ani Atiah Dwi S. | Sr. Analyst - AR & AP Accounting | HO | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Ani Atiah Dwi S. | Sr. Analyst - AR & AP Accounting | HO | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Ani Atiah Dwi S. | Sr. Analyst - AR & AP Accounting | HO | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Arif Prasetyo | Specialist EM Planning HO | HO | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Asgap bin Ali | Finance Coordinator | Surabaya | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Asgap bin Ali | Finance Coordinator | Surabaya | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
August Triyanto | Sr. Specialist - Warranty | HO | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
August Triyanto | Sr. Specialist - Warranty | HO | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
August Triyanto | Sr. Specialist - Warranty | HO | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Bagus Ardianto | Accounting Supervisor | Tanjung - South Kalimantan | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Brenda Chua | PSC | TUS | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Brenda Chua | PSC | TUS | UAT-PSL-002 | 1.5 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Budi Kepri Siagian | Counterman | POD HOBU Tembagapura | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Budi Rustianto | PPSC Planner (R2B) | HO | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Candra Juliawan | Parts Foreman | CRC Parts Ops | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Dayang Kardina Lubis | Specialist Master Data and Product Costing HO | HO | UAT-FIN-001 | 3 | 2018-03-14 | 2018-03-16 | bar: 2018-03-14 to 2018-03-16
Dayang Kardina Lubis | Specialist - Master Data & Prod. Cost. | Finance Head Office | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Dayang Kardina Lubis | Specialist - Master Data & Prod. Cost. | Finance Head Office | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Dayang Kardina Lubis | Specialist - Master Data & Prod. Cost. | Finance Head Office | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Dayang Kardina Lubis | Specialist - Master Data & Prod. Cost. | Finance Head Office | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Defrianto Victor Mantong | Analyst Accounting | HO East Indonesia | UAT-PSL-003 | 1.5 | 2018-03-07 | 2018-03-08 | bar: 2018-03-07 to 2018-03-08
Dimas Rah Utomo | Warehouseman Foreman | Tanjung - South Kalimantan | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Doddy Agung Cahyono | Senior Supervisor Accounting | Banjarmasin | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Dony Juaeni | Finance Supervisor | Batu Hijau | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Dovi Achmad Jauhari | Analyst Service Account | HUB Operations North Sumatra | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Eko Prihardiyanto | Counterman | CRC Parts Ops | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Eko Yanuarto | Event Planner | SCC East Java | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Elisa Grandhy Gunawan | Senior Supervisor EM Strategy HO | HO | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Erwin Romadhoni | Product Support Sales Reps | Palembang | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Fernando Hutabarat | Senior Analyst Master Data and Product Costing HO | HO | UAT-FIN-001 | 3 | 2018-03-14 | 2018-03-16 | bar: 2018-03-14 to 2018-03-16
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Fernando Hutabarat | Sr. Analyst -Master Data & Prod. Costing | Finance Head Office | UAT-FIN-002 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Fitriasti Eka Primasantri | Accounting Assistant | HO West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Gigih Ananto | Sr. Analyst Accounting | Balikpapan | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Habibi Bachtiar | Analyst Technical Communication | Pontianak | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Hany Anggut Abdullah Saleh Kholagi | Analyst Finance | Batu Hijau | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Hany Anggut Abdullah Saleh Kholagi | Analyst Finance | Batu Hijau | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
Harseto Uda Baitti | Analyst Service Operations | Kendari | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Harseto Uda Baitti | Analyst Service Operations | Kendari | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Harseto Uda Baitti | Analyst Service Operations | East Indonesia - Kendari | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-PSC-001 | 1 | 2018-03-14 | 2018-03-14 | bar: 2018-03-14
MARLIN AMBARURA (replacing I Nengah Sumantra) | Specialist Service Operations | MRC - Service Accounts | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Imelda Lumembang Sanapang | Supervisor Service | CRC Balikpapan | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Irawan Kuswenda | Supervisor Parts | Kalimantan Operations - EMP Parts Operation | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Irvina Mamuaya | Senior Analyst Service Account | Manado | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Irvina Mamuaya | Senior Analyst Service Account | Manado | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Jefta Hendrik | Accounting Supervisor | HO East Indonesia | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Jefta Hendrik | Accounting Supervisor | Manado | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
VEKY PALENEWEN (replacing Join Bernard Lasut) | Parts Operation Supervisor | Parts Warehouse Lowland | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
VEKY PALENEWEN (replacing Join Bernard Lasut) | Parts Operation Supervisor | Parts Warehouse Lowland | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
Karen Cheong | Account Executive | TUS | UAT-PSL-002 | 1.5 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Kemas Triseptheo | Counterman | Bangka Belitung | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Kemas Triseptheo | Counterman | Bangka Belitung | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Kemas Triseptheo | Counterman | Bangka Belitung | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Kiswanto | Senior Analyst Warehouse & Distribution | HO | UAT-PSC-001 | 1 | 2018-03-14 | 2018-03-14 | bar: 2018-03-14
Leo Baskara Sjahril | Senior Analyst Parts Operations | HO | UAT-PSC-002 | 1 | 2018-03-09 | 2018-03-09 | bar: 2018-03-09
Leonardo Pomantau | Accounting Sr. Specialist | HO Tembagapura | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Leonardo Pomantau | Accounting Sr. Specialist | HO Tembagapura | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Lia Muliana | Analyst Tax Operations | HO | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
LEONARDO POMANTOW (replacing) Lidia Prischie Liud | Accounting Senior Specialist | AR & Reporting | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Lidia Prischie Liud | Accounting Specialist | HO Tembagapura | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Lidia Prischie Liud | Accounting Specialist | HO Tembagapura | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
M. Andi Azis Nur Abdillah | Parts Analyst | Batu Kajang - South Kalimantan | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
M. Andi Azis Nur Abdillah | Parts Analyst | Batu Kajang - South Kalimantan | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Mantasiah | Analyst Parts Operation | Sorong | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Mantasiah | Analyst Parts Operation | Sorong | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Martina Dwi Rahayu | Analyst Component Management Major | Parts Supply Chain HO | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Martina Dwi Rahayu | Analyst Component Management Major | Parts Supply Chain HO | UAT-FIN-002 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Martina Dwi Rahayu | Analyst Component Management Major | Parts Supply Chain HO | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Mathius Jhon Tangdilallo | Specialist Warranty | Sanggata - North Kalimantan | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Matius Mongan | Parts Operations Supervisor | Manado | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Mia Amelia | Specialist AR/AP Accounting | HO | UAT-PSC-001 | 1 | 2018-03-14 | 2018-03-14 | bar: 2018-03-14
Mia Amelia | Specialist AR/AP Accounting | HO | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Mia Amelia | Specialist AR/AP Accounting | HO | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Mia Amelia | Specialist AR/AP Accounting | HO | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Mia Amelia | Specialist AR/AP Accounting | HO | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Mita Restiana | Specialist - Fixed Asset Management | HO | UAT-FIN-001 | 3 | 2018-03-14 | 2018-03-16 | bar: 2018-03-14 to 2018-03-16
Mita Restiana | Specialist - Fixed Asset Management | HO | UAT-FIN-002 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Mita Restiana | Specialist - Fixed Asset Management | HO | UAT-PSC-002 | 1 | 2018-03-09 | 2018-03-09 | bar: 2018-03-09
Mita Restiana | Specialist - Fixed Asset Management | HO | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Moch Fauzie Farid | Finance Analyst | CRC Finance | UAT-CS-009 | 2 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Mohammad Esa Praditya | Specialist Contract Performance | HO | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Mohammad Esa Praditya | Specialist Contract Performance | HO | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Mohammad Esa Praditya | Specialist Contract Performance | HO | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Mohammad Esa Praditya | Specialist Contract Performance | HO | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Muh Rizal Adam | Specialist Service Operations | Kalimantan Operations - EMP | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Muhammad Afriansyah | Senior Analyst Finance | Sanggata - North Kalimantan | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Muhammad Afriansyah | Senior Analyst Finance | Sanggata - North Kalimantan | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Muhammad Afriansyah | Senior Analyst Finance | Sanggata - North Kalimantan | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-003 | 1.5 | 2018-03-07 | 2018-03-08 | bar: 2018-03-07 to 2018-03-08
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Muhammad Ardi | Senior Analyst Tax Operations | HO | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Muhammad Faisal Rachman | Specialist Warranty | North Kalimantan - Balikpapan | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Muhammad Nasrun Tasman | Parts Operation Supervisor | North Kalimantan - Balikpapan | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Muhammad Nasrun Tasman | Parts Operations Supervisor | North Kalimantan - Balikpapan | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Muhammad Nurul Yaqin | Parts Operations Supervisor | HUB Operations East Java | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Muhammad Nurul Yaqin | Parts Operations Supervisor | HUB Operations East Java | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Muliono | Specialist Warranty | HUB Operations South Sumatra | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Mustafa | Specialist Parts Inventory (Supply Planning HO) | HO | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Mustafa | Specialist Parts Inventory (Supply Planning HO) | HO | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Muswar | Supervisor Parts Counter Operations | Product Support - Tembagapura | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Muswar | Supervisor Parts Counter Operations | Product Support - Tembagapura | UAT-PSL-004 | 1 | 2018-02-28 | 2018-02-28 | bar: 2018-02-28
Nadya Patricia | Specialist Service Account | Balikpapan | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Nadya Patricia | Speicialist Service Account | North Kalimantan - Balikpapan - Service Account | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Nandang Somara | Event Planner Senior Analyst (Service Advisor) | SCC West Java | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Nandang Somara | Event Planner Senior Analyst (Service Advisor) | SCC West Java | UAT-CS-012 | 1 | 2018-02-23 | 2018-02-23 | bar: 2018-02-23
Nandini Swasti Achedya Chandraditya | Sales Administration | HO North Kalimantan | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Parid Durachin | Counterman | Balikpapan | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Parid Durachin | Counterman | Balikpapan | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Parsaoran Siahaan | Warehouseman | Sanggata - North Kalimantan | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Parsaoran Siahaan | Warehouseman | Sanggata - North Kalimantan | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Patriyani | Sr. Specialist Service Operation | Batu Hijau - Service Support | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Perdana Amir Rozaq | Supplier Interface and Pricing Specialist HO | HO | UAT-FIN-002 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13
Perdana Amir Rozaq | Supplier Interface and Pricing Specialist HO | HO | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Prastuty Wahyuningtyas | Senior Analyst Service Account | HUB Operations East Java | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Prastuty Wahyuningtyas | Senior Analyst Service Account | HUB Operations East Java | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Putut Suryono | Parts Operations Supervisor | POD HOBU Tembagapura | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Rachmawaty Husein | Specialist Parts Inventory (Supply Planning HO) | HO | UAT-PSC-001 | 1 | 2018-03-14 | 2018-03-14 | bar: 2018-03-14
Ragil Prasetyo | Analyst Master Data & Production Cost | HO | UAT-PSC-001 | 1 | 2018-03-14 | 2018-03-14 | bar: 2018-03-14
Ragil Prasetyo | Analyst - Master Data & Prod. Cost. | Finance Head Office | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Ragil Prasetyo | Analyst - Master Data & Prod. Cost. | Finance Head Office | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Ragil Prasetyo | Analyst - Master Data & Prod. Cost. | Finance Head Office | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Rahadian Sukma | Sales Supervisor | Padang | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Rizali Hadi | Sr. Analyst Strategy | Banjarmasin | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Ryan Thong | Assistant Executive Parts TUS | TUS | UAT-PSL-002 | 1.5 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Ryan Thong | Assistant Executive Parts TUS | TUS | UAT-PSL-007 | 1.5 | 2018-02-21 | 2018-02-22 | bar: 2018-02-21 to 2018-02-22
Selvy Rompas | Senior Specialist Service Operation | Product Support - Tembagapura | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Selvy Rompas | Senior Specialist Service Operation | Product Support - Tembagapura | UAT-CS-011 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Slamet Supriyono | Senior Analyst Tools Asset Management | HO | UAT-PSC-002 | 1 | 2018-03-09 | 2018-03-09 | bar: 2018-03-09
Stephanus Mas Agung Dewantoro | Accounting Manager | Soroako | UAT-PSL-009 | 1.5 | 2018-02-23 | 2018-02-26 | bar: 2018-02-23; 2018-02-26
Steven Tamalonggehe | Specialist Service Account | Batu Kajang - South Kalimantan | UAT-CS-005 | 2 | 2018-02-19 | 2018-02-20 | bar: 2018-02-19 to 2018-02-20
Sudaryono | Senior Supervisor Service | MRC Kalimantan Operations | UAT-CS-010 | 2 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
RONNY KUMENDONG (replacing Sudirman) | Senior Specialist Strategy | GRS Ops - Service Support | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Sukarno Rachmat Hidayat | Senior Analyst Service Operations | Balikpapan Service Operation | UAT-CS-013 | 1 | 2018-02-13 | 2018-02-13 | bar: 2018-02-13
Suryadana Atma Raharja | Specialist Parts Operation (Demand Planning HO) | HO | UAT-PSL-001 | 2 | 2018-03-01 | 2018-03-02 | bar: 2018-03-01 to 2018-03-02
Syachrun Daude | Analyst Accounting | Soroako | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Tihara Setia Ningrum | Analyst - Funding & Liquidity Mgmt | Finance Head Office | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Titik Widowati Nugraheni | Parts Advisor | Surabaya | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Wahyu Prio Handoko | Parts Operations Foreman | Tanjung - South Kalimantan | UAT-PSL-005 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Wahyuddin Kandu | Manager Finance Strategy Controller | HO | UAT-FIN-001 | 3 | 2018-03-14 | 2018-03-16 | bar: 2018-03-14 to 2018-03-16
Warno | Office Operation Assistant | HRGA - West Java | UAT-CS-004 | 3 | 2018-03-07 | 2018-03-09 | bar: 2018-03-07 to 2018-03-09
Warno | Office Operation Assistant | HRGA - West Java | UAT-CS-006 | 3 | 2018-02-21 | 2018-02-23 | bar: 2018-02-21 to 2018-02-23
Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-PSL-006 | 1.5 | 2018-02-12 | 2018-02-13 | bar: 2018-02-12 to 2018-02-13
Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-PSL-008 | 1.5 | 2018-02-14 | 2018-02-15 | bar: 2018-02-14 to 2018-02-15
Yudi Syarif | Parts Operations Supervisor | Makassar | UAT-CS-003 | 2 | 2018-03-05 | 2018-03-06 | bar: 2018-03-05 to 2018-03-06
Yudi Syarif | Parts Operations Supervisor | Makassar | UAT-PSL-003 | 1.5 | 2018-03-07 | 2018-03-08 | bar: 2018-03-07 to 2018-03-08
Yulman Supriansyah | Analyst Warranty | HUB Operations East Java | UAT-CS-001 | 2 | 2018-02-26 | 2018-02-27 | bar: 2018-02-26 to 2018-02-27
Yulman Supriansyah | Analyst Warranty | HUB Operations East Java | UAT-CS-002 | 3 | 2018-02-28 | 2018-03-02 | bar: 2018-02-28 to 2018-03-02
Zulfikar Al Ahmad | Senior Analyst Service Operations | HUB Operations South Sumatra | UAT-CS-008 | 2 | 2018-03-15 | 2018-03-16 | bar: 2018-03-15 to 2018-03-16
Zulhamdyanov | Analyst Parts Operations | Pekanbaru | UAT-CS-007 | 2 | 2018-03-12 | 2018-03-13 | bar: 2018-03-12 to 2018-03-13

## Duplicate (hidden)
No | Name | Position | Office | Scenario | Duration | UAT Start Date | UAT End Date | [54 empty] | Region/Site | PIC Integration | PIC Support | time axis 2018-02-05 to 2018-03-30
2 | Asgap bin Ali | Finance Coordinator | Surabaya | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Asgap bin Ali | Finance Coordinator | Surabaya | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
5 | Jefta Hendrik on behalf of Nur Asri Syahrir | Finance Manager | HO East Indonesia | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Jefta Hendrik | Accounting Supervisor | Manado | UAT-CS-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
8 | Lidia Prischie Liud | Accounting Specialist | HO Tembagapura | UAT-CS-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Lidia Prischie Liud | Accounting Specialist | HO Tembagapura | UAT-CS-011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Lidia Prischie Liud | Accounting Specialist | HO Tembagapura | UAT-PSL-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
10 | Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-CS-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-PSL-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudhistira | Senior Analyst Finance | HO South Sumatra | UAT-PSL-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
11 | Leonardo Pomantau | Finance Manager | HO Tembagapura | UAT-CS-011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Leonardo Pomantau | Finance Manager | HO Tembagapura | UAT-PSL-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
18 | Bahruzar | Senior Supervisor Accounting | HO South Sumatra | UAT-PSL-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Bahruzar | Senior Supervisor Accounting | HO South Sumatra | UAT-PSL-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
19 | Muhammad Afriansyah | Senior Analyst Finance | Sanggata - North Kalimantan | UAT-PSL-007 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muhammad Afriansyah | Senior Analyst Finance | Sanggata - North Kalimantan | UAT-PSL-009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
23 | Moch Fauzie Farid | Finance Analyst | CRC Finance | UAT-CS-009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Moch Fauzie Farid | Finance Analyst | CRC Finance | UAT-CS-010 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
24 | Astrid Fourlia L. Tobing | Acccouting Supervisor | HO North Kalimantan | UAT-CS-009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Astrid Fourlia L. Tobing | Acccouting Supervisor | HO North Kalimantan | UAT-CS-010 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-CS-012 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Henki Irwan | Supervisor Parts | HUB Operations West Java | UAT-PSC-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muhammad Nurul Yaqin | Parts Operations Supervisor | HUB Operations East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muhammad Nurul Yaqin | Parts Operations Supervisor | HUB Operations East Java | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudi Syarif | Parts Operations Supervisor | Makassar | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudi Syarif | Parts Operations Supervisor | Makassar | UAT-PSL-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Warno | Clerk Purchasing Reps | HRGA - West Java | UAT-CS-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Warno | Clerk Purchasing Reps | HRGA - West Java | UAT-CS-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-PSL-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-CS-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudha Winandar | Coordinator Warehouse | HUB Operations South Sumatra | UAT-PSL-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yudha Winandar on behalf of Iswardi | Warehouseman | HUB Operations South Sumatra | UAT-CS-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Join Bernard Lasut | Parts Operations Foreman | POD LOBU Tembagapura | UAT-CS-011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Join Bernard Lasut | Parts Operations Foreman | POD LOBU Tembagapura | UAT-PSL-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muhammad Nasrun Tasman | Parts Operations Supervisor | Balikpapan | UAT-CS-013 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muhammad Nasrun Tasman | Parts Operations Supervisor | Balikpapan | UAT-CS-010 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Andhik Pujianto | Senior Analyst Strategy | EM Batuhijau | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Andhik Pujianto on behalf of Luluk Setiono | PS Region Manager | Surabaya | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Andhik Pujianto on behalf of Azkhwaldi Aziz Chan | Region Manager | HO East Java | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Ryan Thong | Assistant Executive Parts TUS | TUS | UAT-PSL-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Ryan Thong | Assistant Executive Parts TUS | TUS | UAT-PSL-007 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Parsaoran Siahaan | Warehouseman | Sanggata - North Kalimantan | UAT-PSL-007 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Parsaoran Siahaan | Warehouseman | Sanggata - North Kalimantan | UAT-PSL-009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Nandang Somara | Event Planner Senior Analyst (Service Advisor) | SCC West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Nandang Somara | Event Planner Senior Analyst (Service Advisor) | SCC West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Nandang Somara | Event Planner Senior Analyst (Service Advisor) | SCC West Java | UAT-CS-012 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Ardian Rinto Nugroho | Supervisor Service Operations | HUB Operations West Java | UAT-CS-012 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Habibi Bachtiar | Analyst Technical Communication | Pontianak | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Habibi Bachtiar | Analyst Technical Communication | Pontianak | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yulman Supriansyah | Analyst Warranty | HUB Operations East Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yulman Supriansyah | Analyst Warranty | HUB Operations East Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Yulman Supriansyah | Analyst Warranty | HUB Operations East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Eko Yanuarto | Event Planner | SCC East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Eko Yanuarto | Event Planner | SCC East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Prastuty Wahyuningtyas | Senior Analyst Service Account | HUB Operations East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Prastuty Wahyuningtyas | Senior Analyst Service Account | HUB Operations East Java | UAT-CS-002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Harseto Uda Baitti | Analyst Service Operations | Kendari | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Harseto Uda Baitti | Analyst Service Operations | Kendari | UAT-CS-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Irvina Mamuaya | Senior Analyst Service Account | Manado | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Irvina Mamuaya | Senior Analyst Service Accoun | Manado | UAT-CS-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Irvina Mamuaya on behalf of Achmad Ridjaluddin | Region Manager | Makassar | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Selvy Rompas | Senior Specialist Service Operation | Product Support - Tembagapura | UAT-CS-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Selvy Rompas | Senior Specialist Service Operation | Product Support - Tembagapura | UAT-CS-011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-CS-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-CS-012 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Gatot Priyo Nugroho | Parts Operation Supervisor / Event Planner | BSD / SCC West Java | UAT-PSL-001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Mantasiah | Analyst Parts Operation | Sorong | UAT-CS-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Mantasiah | Analyst Parts Operation | Sorong | UAT-CS-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Mantasiah | Analyst Parts Operation | Sorong | UAT-PSL-003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| M. Andi Azis Nur Abdillah | Parts Analyst | Batu Kajang - South Kalimantan | UAT-CS-005 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| M. Andi Azis Nur Abdillah | Parts Analyst | Batu Kajang - South Kalimantan | UAT-PSL-005 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Kemas Triseptheo | Counterman | Bangka Belitung | UAT-CS-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Kemas Triseptheo | Counterman | Bangka Belitung | UAT-PSL-006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Kemas Triseptheo | Counterman | Bangka Belitung | UAT-PSL-008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muswar | Supervisor Parts Counter Operations | Product Support - Tembagapura | UAT-CS-011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Muswar | Supervisor Parts Counter Operations | Product Support - Tembagapura | UAT-PSL-004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Parid Durachin | Counterman | Balikpapan | UAT-CS-013 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| Parid Durachin | Counterman | Balikpapan | UAT-CS-010 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!

## Dependency (hidden)
UAT-CS-003 | UAT-PSL-002* | UAT-CS-009 | UAT-PSL-006 | UAT-CS-005 | UAT-CS-006 | UAT-CS-001
UAT-CS-004 | UAT-PSL-007 | UAT-CS-010 | UAT-PSL-008 | UAT-PSL-005 | UAT-CS-011* | UAT-CS-002
[5 empty] | Selvy Rompas | Habibi Bachtiar
UAT-CS-003 | UAT-PSL-007 | UAT-CS-013 | UAT-PSL-006
UAT-PSL-003 | UAT-PSL-009 | UAT-CS-010 | UAT-CS-008 |  | UAT-CS-006
|  |  | UAT-PSL-008 |  | UAT-CS-011*
UAT-PSL-004
UAT-CS-003 |  |  |  |  | Lidia Prischie Liud
UAT-CS-004
UAT-PSL-003
UAT-CS-011*
UAT-PSL-004
Leonardo Pomantau
Join Bernard Lasut
Muswar
Conflict
| CS-005 | CS-003
| CS-007 | CS-004
SPM Related
PCS-011
PSL-002
PSC-001