## 3W
| Date, time : |  | 27/03/2019, 1300-1700
| Attendees : |  | Merdeka Copper Gold (MCG) |  | Caterpillar (CAT) |  | TU |  | TUS
|  |  | Richard Schloss (RS) |  | Imam Perkasa (IP) |  | Azkhwaldi Aziz (Aldi) |  | Tim Day (TD)
|  |  | Yusnita Widiarti (YW) |  |  |  | Tema Mendrofa (TM) |  | Mariana (Mrn)
|  |  | Nugraha Pamungkas (NP) |  |  |  | Daniel Douglas (DD)
|  |  | Rommy Putra (RP) |  |  |  | Pramono Wardoyo (PW)
Mario Rais (MR)
Ivan Gultom (IG)
| Venue : |  | Westin Hotel, Padang Room 2, Level One. Jakarta |  |  |  | Subject : | Merdeka-Trakindo Collaboration Level Set Meeting
ACTIVITY |  | No | TASK | PIC |  | TEAM | WHEN (Completion Date) |  | COMMENTS | PROGRESS
[7 empty] | Target | Actual
|  |  | RGE/CAT Alliance Response |  | Phil Pollock | CAT | asap |  | Phil Pollock to call Devanesan tomorrow, 21st Apr 16
|  | 1 | Welcome | Tim Day |  | TU Spore |  |  |  | on going
|  | 2 | General Safety | Tim Day |  | TU Spore |  |  |  | on going
|  | 3 | Update on Order Status Report TU | Mariana |  | TU Spore |  |  |  | on going
|  | 4 | Update on Order Status Report TUS | Mariana |  | TU Spore |  |  |  | on going
|  | 5 | 6015 Duty exemption | Mariana |  | TU Spore |  |  |  | on going
|  | 6 | 2x6015 Offloading + future offloading | Tim Day |  | TU Spore |  |  |  | on going
|  | 7 | 2x6015 TB&W Non Cat Option Fitment | Daniel Douglas |  | TU Jakarta |  |  |  | on going
|  | 8 | 1x6015 TB Non Cat Option Fitment | Daniel Douglas |  | TU Jakarta |  |  |  | on going
|  | 9 | 13x745 TB Non Cat Option Fitment | Daniel Douglas |  | TU Jakarta |  |  |  | on going
|  | 10 | Update on Tooling/CAT SIS | Daniel Douglas |  | TU Jakarta |  |  |  | on going
|  | 11 | Term Sheet and Product Support Agreement | John Noreiks |  | TU Jakarta |  |  |  | done
|  | 12 | Dedicated Merdeka Product Support Go To Person in Jakarta | Daniel Douglas supported by Russel Nolan |  | TU Jakarta |  |  |  | on going
|  | 13 | Update on quote for Non Cat Options for all other machines | Daniel Douglas/Aldi/Tema |  | TU Jakarta/TU Sby |  |  |  | on going
|  | 14 | Update on operator training package | Aldi/Ivan Gultom |  | TU Sby |  |  |  | done
|  | 15 | Update on 745 back up machine - Terms & Conditions/ Rent rate if available for rent/ Purchase price formula after two years | Peter Docherty |  | TU Jakarta |  |  |  | done
|  | 16 | Update on Tujuh Bukit implementation | Ivan Gultom |  | TU Sby |  |  | Currently site support already established | on going
|  | 17 | Quote 3x bucket 2.5cum for 966H Wetar | Aldi |  | TU Sby |  |  |  | in progress with John Eckhart
|  | 18 | Update on GAP order for GET/UC | Ivan Gultom |  | TU Sby |  |  |  | on going
|  | 19 | Stock List (GET/UC) in Kupang | Ivan Gultom |  | TU Sby |  |  | No stock in Kupang | done
|  | 20 | Operator Training | Aldi |  | TU Sby |  |  |  | done
|  | 21 | Quote on Maintenance Training | Ivan Gultom |  | TU Sby |  |  |  | in progress
|  | 22 | Apprentice System, Trakindo Involvement | Tema |  | TU Java Division |  |  |  | done
|  | 23 | General Discussion | all
Design
Note
How does TUS translate sales opportunity to sales funnel
SL/Mrn to provide lead and translate to sales opportunity, Shanmugam will follow up and translate to quotation