## Preparation
Persiapan SAT & MSR MARC PTSI (3 - 7 October 2022)
MoM Meeting 14 Sep 2022
No | Activity | PIC | Target | Completion | Remark
I | General Preparation
1 | Itinerary & Team Member | Mukhlisin | 2022-09-14 | Done
2 | Meeting room SAT&MSR | Gunawan | 2022-09-16 |  | Meeting room customer, TU Tesso
3 | Infocus | Gunawan | 2022-09-14 | Done
4 | Akomodasi hotel (Hotel Fox) | Kemal | 2022-09-23
5 | Transportasi | Gunawan | 2022-09-30 |  | Mobil Kemal, Mobil ops TU Tesso
6 | APD (Safety shoes, helmet, masker) | All | 2022-09-30 |  | Safety Vest (order), helmet PKU
7 | Vaksin Booster & Peduli Lindungi | All | 2022-09-30 | Done
8 | Akomodasi Tesso | Kemal | 2022-09-30
II | Preparation SAT
A | Machine Application
1 | Data PSRPT | M. Indra | 2022-09-14 |  | Traver ratio, utilisasi, fuel burn, abuse
2 | Data SAT Oct 2021 | Patrisius Joko | 2022-09-20
3 | GPS | Patrisius Joko | 2022-09-26 |  | Pinjam dari Apps Eng
4 | Data production SPHead (actual vs target) | Gunawan | 2022-09-23
B | Maintenance & Repair
1 | Check list M&R | Patrisius Joko | 2022-09-20 |  | kirim check list 2021 ke Gunawan
2 | Pembagian task list per PIC | Syamsul | 2022-09-14 |  | Application: Conerisman, Joko, Gunawan, Akbar, Budi SP, M. Ari Maintenance: Heppy, Syamsul, M.Indra, Mukhlisin, Wisnhu
3 | Print out check list berdasarkan task list | Gunawan | 2022-09-30 |  | Pekanbaru
III | Preparation MSR
1 | Data previous MSR 2021 | Wisnhu | 2022-09-14 | Done
2 | Data Fleet Performance | Alip | 2022-09-28 |  | Compare MSR 2021 vs 2022, by fleet
3 | Data Financial Performance | Wisnhu | 2022-09-20 |  | Compare MSR 2021 vs 2022, by fleet
4 | PPT | M. Ari | 2022-09-28 |  | Operator abuse, CLCA
5 | CLCA | Wisnhu | 2022-09-28 |  | Major component, Engine Midlife, Cylinder
6 | Data file MSR update | M. Ari | 2022-09-28

## Check list
Participant | TCAR | Vaksin Booster | Helmet | Safety Shoes | Safety Vest | Glasses | Infocus
Syamsul Bachru |  | Ö |  |  |  |  | Ö | Ö
Budi Setyo Pranggono |  | Ö
Muhammad Indra Priyatna |  | Ö
Conerisman |  | Ö
Patrisius Joko |  | Ö
Wisnhu Purbowaseso |  | Ö
Muhammad Ari Iskandar |  | Ö
Mukhlisin |  | Ö
Total | 8 | 8 |  |  |  |  | 1

## Itinerary
Itinerary SAT & MSR MARC PTSI 2022
Tanggal | Hari | Lokasi | Rencana Perjalanan | Team SAT & MSR
2022-10-02 | Minggu | Jakarta | Perjalanan Jakarta - Pekanbaru | 1 | Kemal Anshori | Site Head
2022-10-03 | Senin | Pekanbaru | Perjalanan Pekanbaru - Tesso | 2 | Syamsul Bachru | EM Area SUM
|  | Tesso/ Baserah | Safety Induction | 3 | Gunawan | EM Site Leader
|  |  | Overview SAT PTSI | 4 | Heppy Mustika | Service Site Leader
|  |  | SAT Day-1 | 5 | Budi Setyo Pranggono | Technical Solution C&F HO
2022-10-04 | Selasa | Tesso/ Baserah | SAT Day-2 | 6 | Muhammad Indra Priyatna | EM ConMon - C&F HO
|  |  |  | 7 | Conerisman | Cust. Solution C&F HO
2022-10-05 | Rabu | Pekanbaru | Overview MSR TSS | 8 | Patrisius Joko | Prod. Solution C&F HO
|  |  | MSR Day-1 | 9 | Wisnhu Purbowaseso | EM Planning - C&F HO
2022-10-06 | Kamis | Pekanbaru | MSR Day-2 | 10 | Muhammad Ari Iskandar | EM Planning - C&F HO
2022-10-07 | Jumat | Pekanbaru | MSR Day-3, 3W, Summary & Closing | 11 | Mukhlisin | EM C&F HO
2022-10-08 | Sabtu | Pekanbaru | Perjalanan Pekanbaru - Jakarta